## User Stories
ID | Epic | Owner | Title | User Story | Acceptance Criteria | Notes for Claude Code
A1 | A - Infrastructure Setup | You | Create GitHub repository | As the developer, I want a dedicated GitHub repository for this project, so that Claude Code and I have a version-controlled home for the codebase. | - New GitHub repo created (e.g., all-play-standings) with a default branch - Public or private, your call — the app itself is open-access regardless - Repo URL captured for later stories to reference | No coding decisions here — pure account setup.
A2 | A - Infrastructure Setup | You | Create Vercel project, link to repo | As the developer, I want a Vercel project linked to the GitHub repo, so that pushes trigger automatic deployments. | - Vercel project created and connected to the GitHub repo - Auto-deploy on push to main branch confirmed working (even with placeholder content) - Vercel project URL captured | Hobby plan is sufficient — native 1x/day cron (used later in D1) is available on Hobby.
A3 | A - Infrastructure Setup | You | Create Supabase project | As the developer, I want a dedicated Supabase project, so that the app has a Postgres database and API to read from and write to. | - New Supabase project created for this app - Connection string / API URL and anon + service keys retrieved and stored securely (not yet in code) | n/a
A4 | A - Infrastructure Setup | Claude Code | Scaffold Next.js app | As the developer, I want a scaffolded Next.js app (App Router, TypeScript, Tailwind) with a placeholder homepage, so that there's a deployable foundation to build features on. | - App created using App Router + TypeScript + Tailwind - Builds and runs locally without errors - Deploys successfully to the linked Vercel project; placeholder homepage renders at the Vercel URL - Repo structure is reasonably organized | You choose exact folder structure, linting/formatting setup, and starter conventions. No need to add routing for the three tabs yet — scaffolding only. Confirm .gitignore covers .env* files (A5/A6 depend on this).
A5 | A - Infrastructure Setup | You | Retrieve and store ESPN cookies | As the developer, I want my espn_s2 and SWID cookies stored as environment variables, so that later API calls can authenticate to ESPN on my behalf. | - espn_s2 and SWID values retrieved from browser dev tools for a logged-in ESPN Fantasy session - Both added as environment variables in Vercel (Production + Preview as needed) - Both added to local .env.local - .env.local confirmed gitignored | n/a
A6 | A - Infrastructure Setup | Claude Code | Supabase client + env wiring | As the developer, I want the Supabase client library installed and configured to read connection details from environment variables, so that later features can read/write to the database without additional setup. | - Supabase client library installed and initialized in the app - Client reads Supabase URL/key from environment variables (not hardcoded) - A simple connectivity check (e.g., health-check route) confirms the app can reach the Supabase project - .env.example file added listing required variable names (no real values) | Your call whether to use the Supabase JS client directly or a lightweight wrapper. No schema exists yet (that's C1) — this is plumbing only.
B1 | B - ESPN Data Integration | Claude Code | ESPN API client — league metadata | As the app, I want to fetch league metadata (teams, names/logos, current week, matchup schedule) from ESPN's API using stored cookies, so that the app knows who's in the league and what week it is. | - Function/module exists that, given leagueId and season, authenticates with espn_s2/SWID and returns team list (names, logos), current NFL week, and matchup schedule - Verified against the real league (ID 33257291, 2026 season) returns accurate team names - Current week value comes from ESPN's own API field, not a manually reimplemented calendar | Structure as a reusable client module since B2 and later ingestion will call it repeatedly. Caching league metadata (teams rarely change mid-season) is a reasonable idea but your call.
B2 | B - ESPN Data Integration | Claude Code | Fetch box scores for a given week | As the app, I want to fetch each team's point total for a given week, so that all-play comparisons can be computed from real scores. | - Function exists that, given a week number, returns each team's total score for that week - Handles both completed weeks and the in-progress current week (live/partial scores) - Verified against real league data for at least one completed week and the current in-progress week | Return shape should be whatever's most convenient for C2/C3 to consume — your call on the exact interface.
B3 | B - ESPN Data Integration | Claude Code | Error handling for expired/invalid cookies | As the developer, I want a clear error when ESPN cookies are expired or invalid, so that I know to refresh them instead of staring at a silent failure. | - ESPN API calls that fail due to auth (expired/invalid cookies) surface a specific, human-readable error, not a generic 500 or blank page - Error is visible in Vercel logs and, where relevant, in any user-facing error state (ties into F2) - A simulated bad-cookie request is verified to produce this specific error path, not a crash | A shared error type/class used by B1/B2 lets downstream code (ingestion, routes) distinguish 'cookies expired' from other failures — recommended, not mandated.
C1 | C - Database Schema & Data Pipeline | Claude Code | Supabase schema | As the app, I want a database schema for leagues, teams, and weekly scores, so that ingested data has somewhere durable to live. | - Tables created: leagues, teams, weekly_scores - Every table includes a league_id column - weekly_scores captures at minimum: team, week, score, league_id - No all_play_results table (all-play is computed on read) - Schema applied to the Supabase project and confirmed queryable | You decide exact column types, keys, and indexes. Single-league proof of concept — don't over-engineer multi-tenancy beyond the league_id column, just leave the door open.
C2 | C - Database Schema & Data Pipeline | Claude Code | Ingestion API route | As the app, I want an API route that pulls the current week's scores from ESPN and upserts them into weekly_scores, so that the database stays in sync with live scores. | - API route calls B1/B2, then upserts results into weekly_scores (insert new, update existing rows for the same team/week) - Running the route twice in a row for the same week does not create duplicate rows - Route returns a clear success/failure response - Verified end-to-end against the real league: running it populates weekly_scores with real data | This route is what D1 (cron) and D2 (manual refresh) will both call — build it as the single source of truth for ingestion rather than duplicating logic later.
C3 | C - Database Schema & Data Pipeline | Claude Code | All-play calculation logic | As the app, I want to compute a team's all-play win/loss record for a given week by comparing its score against every other team's score, so that the Week tab can display it. | - Given a week's scores for all teams, function returns each team's win/loss tally against every other team (e.g., 11-team league → 10 comparisons per team) - Verified with a hand-checked example (manually confirm one team's win/loss count for one real week matches the function's output) - Handles the in-progress current week using live/partial scores from B2 - Function is pure/testable, not tied to a specific API route | Worth a quick standalone sanity-check script even without a full test suite. Ties are a normal outcome (equal scores are rare but shouldn't crash the function).
C4 | C - Database Schema & Data Pipeline | Claude Code | Season standings aggregation | As the app, I want to sum each team's all-play record across all weeks played so far, including the live current week, so that the Season Standings tab and Playoff Bracket can rank teams. | - Function sums all-play win/loss across every week with data in weekly_scores, using C3's per-week logic - Current in-progress week's live scores are included in the running total - When two teams have identical all-play win/loss records, they are ordered by total points scored (season-to-date), higher first - Verified against a hand-checked example spanning at least two weeks | Output should include whatever E2 (Season Standings) and E3 (Playoff Bracket) both need — e.g., win/loss, win %, points scored, rank. Your call on exact shape.
E1 | E - Frontend | Claude Code | Week tab | As a league member, I want to see all-play results for any week, so that I can see how my team's score stacked up against everyone else that week, not just my scheduled opponent. | - Defaults to current NFL week on load - Dropdown/selector lets me view any prior week with data - For the selected week, table shows each team's all-play win/loss record (e.g., '8-2') and actual score, sorted sensibly - Current/live week visually distinguished per creative brief (LIVE badge) - Verified against real data for at least one completed week | Styled per the creative brief from the start, not retrofitted later. You choose sort order, component structure, and state management approach.
E2 | E - Frontend | Claude Code | Season Standings tab | As a league member, I want to see cumulative all-play standings for the season, so that I know where my team ranks overall. | - Shows every team's cumulative all-play record (season-to-date), sorted by win % then points-scored tiebreaker - Reflects the current week's live scores once ingested (see note on 'real time') - Rank number displayed per team per creative brief (leaderboard treatment) - Verified against C4 output for correctness | 'Real time' means 'reflects latest ingested data,' not live polling — given the 1x/day cron plus manual refresh (D2), the page just needs to be correct whenever it loads.
E3 | E - Frontend | Claude Code | Playoff Bracket tab | As a league member, I want to see a projected playoff bracket based on current all-play standings, so that I can see where my team would land if the season ended today. | - Bracket shows top 6 teams by all-play record (points-scored tiebreaker), seeds 1–6 - Seeds 1–2 shown with a bye, visually distinct per creative brief - Seeds 3–6 filled into first-round matchups - Bracket reflects latest standings data (same standard as E2) - No ESPN head-to-head record used anywhere in seeding logic | You decide bracket matchup pairing convention (e.g., 3v6, 4v5) — standard sports-bracket seeding is fine unless you have a reason to deviate.
E4 | E - Frontend | Claude Code | Mobile-first responsive design | As a league member on my phone, I want all three tabs to be fully usable on a small screen, so that I'm not fighting a desktop layout to check standings from my phone. | - All three tabs render cleanly at common mobile widths (~375–430px) with no horizontal scroll or cut-off content - Tables/bracket remain readable at mobile size; each tab breathes rather than cramming all three views into one screen - Verified at both a mobile viewport and a standard desktop viewport | Mobile-first means designing/building for small screens first, then scaling up — not a breakpoint bolted on afterward.
E5 | E - Frontend | Claude Code | Visual design pass | As a league member, I want the app to feel like a polished sports-broadcast product, so that checking standings feels fun rather than like reading a spreadsheet. | - Palette, typography, and layout follow the creative brief (dark near-black base, one saturated accent, gold reserved for live indicators, condensed/bold numerals for scores) - Live week indicator (pulsing dot/badge) present on Week tab per brief - No default/generic SaaS look (no default Inter-at-default-weights, no pastel rounded cards) - Applied consistently across E1–E3, not just one tab | Build this into E1–E3 as you go, not as a separate restyle pass — listed as its own story mainly to make the acceptance criteria explicit and checkable. Full creative brief is in the backlog doc (palette/typography/layout/motion).
D1 | D - Scheduling | Claude Code | Vercel cron config | As the app, I want a scheduled job that triggers ingestion once a day overnight, so that scores stay reasonably current without manual intervention. | - vercel.json (or equivalent) cron config triggers the C2 ingestion route once daily, overnight - Ingestion route is protected by a shared-secret check (e.g., header token) so it can't be triggered by an unauthenticated request - Verified: cron fires on schedule after deployment (checked via Vercel's cron logs) and successfully calls ingestion | Keep the secret-check mechanism simple (a single env-var token compared on the route). Cadence is 1x/day now; structure the config so bumping frequency later (if the plan upgrades to Pro) is a small change.
D2 | D - Scheduling | Claude Code | Manual refresh endpoint | As the developer, I want a manual 'refresh now' action, so that I can pull current scores on demand during game days when the daily cron hasn't run recently. | - A button (or accessible endpoint) triggers the same ingestion logic as D1 on demand - Calling it updates weekly_scores and the UI reflects new data after refresh - Clearly indicates loading/success/failure state when triggered - Verified: triggering it mid-week updates scores without waiting for the next cron run | Reuse C2 directly rather than duplicating ingestion logic — this is just an alternate trigger. This is the primary way scores stay current during live game windows given the 1x/day cron.
F1 | F - Deployment & Polish | You | Custom domain | As the developer, I want either a custom domain or a confirmed default Vercel URL, so that I have a stable link to share with the league. | - Either a custom domain is connected and resolving to the app, or the default Vercel URL is confirmed working and is the link to be shared | n/a — no coding decision.
F2 | F - Deployment & Polish | Claude Code | Loading/error states | As a league member, I want clear loading and error states, so that I understand what's happening if data is slow or something's broken instead of seeing a blank or broken page. | - Each tab shows a loading state while data is fetching - If the ESPN API is down or ingestion failed, a clear, non-technical message is shown (not a stack trace or blank page) - Expired/invalid cookie errors (from B3) surface a specific, actionable message somewhere visible - Verified by simulating at least one failure case (e.g., temporarily bad env var) and confirming the error state renders | Balance 'public app has no login' against 'developer needs error detail' — your call on what goes to logs only vs. what the public page shows (e.g., generic 'scores temporarily unavailable').
F3 | F - Deployment & Polish | Claude Code | README | As the developer, I want a README covering setup and operations, so that I (or future me) can maintain this app without re-deriving how it works. | - README covers: local dev setup, required env vars (referencing .env.example from A6), how to refresh ESPN cookies when they expire, and how the Vercel cron job works (including how to change its frequency in vercel.json) - A new contributor could follow it to get the app running locally from a fresh clone | Keep it practical/operational rather than exhaustive — this is a proof-of-concept for one league, not an open-source project needing contribution guidelines.